## Test Cases
Label (SIT/UAT/PROD/NA) | Test Case ID | Module/Feature | Priority (High/Medium/Low) | Severity (High/Medium/Low) | Collected from | Test Scenario | Test Case Description | Preconditions (if any) | Test Steps | Test Data (if any) | Expected Result | Test Case Owner | Environment (SIT/UAT/PROD) | Execution Date | Executed By | Actual Result | Status (Pass/ Fail) | Comments/Remarks | Screenshots
SIT | SIT-TC-WEB-BCO-001 | Website / Discount / Promo Code Bank-card Offer | High | Medium | Signed scope F7 / Q-8 | Promo-code entry appears on the order confirmation page | Verify that a user can access the promo-code entry area before Checkout after selecting a ticket item. | Ticket item is configured with a bank-card offer activity; CyberSource MID test setup is prepared; user is on the single-session ticket order confirmation page. | 1. Select a ticket item that supports promo code. 2. Open the order confirmation page. 3. Locate the promo-code area before the Checkout button. |  | 1. A promo-code entry area is displayed. 2. The entry area is placed before Checkout so the user can enter or select a promo code before payment. 3. If no promo code is entered, the order can still proceed to Checkout at the original price. | Antank QA Team | SIT | 2026-07-08 | Evan | As expected | Pass
SIT | SIT-TC-WEB-BCO-002 | Website / Discount / Promo Code Bank-card Offer | High | High | PRD chapter 1 context + Q-3/Q-8 | Valid promo code is recognized and discount is calculated | Verify that a valid promo code is recognized on the order confirmation page and the corresponding bank-card offer is calculated before Checkout. | Promotion activity is associated with a valid promo code and CyberSource MID; the ticket order meets the activity conditions. | 1. Enter a valid promo code in the promo-code field. 2. Click Confirm or Apply. 3. Wait for promo-code validation to complete. 4. Open the discount detail area. |  | 1. Promo-code validation succeeds. 2. The discount detail area shows the corresponding bank-card offer activity. 3. The payable order amount is refreshed based on the discounted amount. 4. The offer is retained as pending use for the current order. | Antank QA Team | SIT | 2026-07-08 | Evan | As expected | Pass | with discount-40， without discount - 50
SIT | SIT-TC-WEB-BCO-003 | Website / Discount / Promo Code Bank-card Offer | High | Medium | PRD chapter 1 context / F8 | Invalid promo code returns a unified failure message | Verify that an incorrectly formatted or non-existent promo code does not change the order amount and returns a unified unavailable message. | User is on the order confirmation page; no promo code has been applied to the order. | 1. Enter an invalid promo code. 2. Click Confirm or Apply. 3. Wait for the promo-code validation result. |  | 1. The system displays "The current promo code is unavailable" or an equivalent unified failure message. 2. The order amount remains unchanged. 3. CyberSource payment validation is not triggered. 4. The user can clear the value and enter another promo code. | Antank QA Team | SIT | 2026-07-08 | Evan | As expected | Pass
SIT | SIT-TC-WEB-BCO-004 | Website / Discount / Promo Code Bank-card Offer | High | Medium | PRD chapter 1 context / F8 | Valid promo code is unavailable for the current order | Verify that a promo code that exists but is not applicable to the current ticket order is not applied and returns a unified unavailable message. | A valid promo code exists for another activity or ticket item; the current order does not meet that activity condition. | 1. Open an order confirmation page that is not eligible for the promo code. 2. Enter the promo code. 3. Click Confirm or Apply. 4. Wait for the promo-code validation result. |  | 1. The system displays "The current promo code is unavailable" or an equivalent unified failure message. 2. The bank-card offer activity is not shown as available for the current order. 3. The payable order amount remains unchanged. | Antank QA Team | SIT | 2026-07-08 | Evan | As expected | Pass
SIT | SIT-TC-WEB-BCO-005 | Website / Discount / Promo Code Bank-card Offer | Medium | Medium | PRD chapter 1 context / Q-3 | Applied promo code can be removed and replaced | Verify that after a user removes an applied promo code, the discount amount is refreshed and another promo code can be applied. | One valid promo code has already been applied to the order. | 1. Click Remove for the current promo code. 2. Wait for the order amount to refresh. 3. Enter another valid promo code. 4. Click Confirm or Apply. |  | 1. After removal, the original offer no longer applies and the order amount is restored or recalculated. 2. After the new promo code is applied, only the new promo code takes effect. 3. The same order does not retain two promo-code offers at the same time. | Antank QA Team | SIT | 2026-07-08 | Evan | As expected | Pass
SIT | SIT-TC-WEB-BCO-006 | Website / Discount / Promo Code Bank-card Offer | Medium | Medium | PRD chapter 1 context | Only one promo-code offer applies to one order | Verify that one order does not apply multiple promo-code offers at the same time. | Two promo codes are available for the current ticket order. | 1. Apply the first promo code. 2. Enter the second promo code in the promo-code field. 3. Click Confirm or Apply. 4. Open the discount detail area. |  | 1. The system does not allow two promo-code offers to be active at the same time. 2. If replacement is allowed, the old offer is removed before the new offer takes effect. 3. The discount details and payable amount reflect only one active promo-code offer. | Antank QA Team | SIT | 2026-07-08 | Evan | As expected | Pass
SIT | SIT-TC-WEB-BCO-007 | Website / Discount / CyberSource Checkout | High | High | Signed scope F7 / Q-6/Q-7/Q-8 | CyberSource Checkout is launched with discounted amount | Verify that after a user applies a promo code and clicks Checkout, the system starts the CyberSource payment flow with the discounted amount. | A valid promo code has been applied to the order; CyberSource success card and MID test setup are prepared. | 1. Apply a valid promo code. 2. Record the discounted payable amount on the order confirmation page. 3. Click Checkout. 4. Wait for the CyberSource payment page or payment flow to load. |  | 1. CyberSource Checkout is launched successfully. 2. The payment amount is the discounted amount. 3. The payment request or test log uses the expected merchant or MID test configuration. 4. The website does not perform additional BIN or issuer-list validation before CyberSource. | Antank QA Team | SIT | 2026-07-08 | Evan | As expected | Pass
SIT | SIT-TC-WEB-BCO-008 | Website / Discount / CyberSource Checkout | High | High | Signed scope F7 / Q-6/Q-7 | Order succeeds after successful CyberSource payment | Verify that when the MID and card payment gateway test setup match, the order is paid successfully after CyberSource returns success. | Valid promo code has been applied; CyberSource success test card is available for the matched MID. | 1. Click Checkout to enter CyberSource. 2. Complete payment with the success test card. 3. Return to the website. 4. Open the order detail page. |  | 1. CyberSource returns a successful payment result. 2. The website order status is Paid or Payment Successful. 3. The order payment amount equals the discounted amount. 4. The order detail retains the promo code or offer activity record. | Antank QA Team | SIT | 2026-07-08 | Evan | As expected | Pass
SIT | SIT-TC-WEB-BCO-009 | Website / Discount / CyberSource Checkout | High | High | Signed scope F8 / Q-6/Q-7 | MID, card, or gateway mismatch causes payment failure | Verify that when the MID, card, or payment gateway setup does not match, the system follows the CyberSource failure result and does not treat the order as paid. | Valid promo code has been applied; unmatched MID or failure test card is prepared. | 1. Click Checkout to enter CyberSource. 2. Pay with an unmatched or failure test card. 3. Return to the website. 4. Open the order detail page. |  | 1. CyberSource returns failure or a non-success result. 2. The website order does not enter paid status. 3. Successful tickets are not issued. 4. The user can retry payment or return to modify the promo code. | Antank QA Team | SIT | 2026-07-10 | Evan | As expected | Pass | failed and retried 5200000000002151
SIT | SIT-TC-WEB-BCO-009 | Website / Discount / CyberSource Checkout | High | High | Signed scope F8 / Q-6/Q-7 | MID, card, or gateway match, then payment success | Verify that when the MID, card, or payment gateway setup match, the system follows the CyberSource to pay with success | Valid promo code has been applied with the payment gateway | 1. Click Checkout to enter CyberSource. 2. Pay with a specific mid / gateway / BIN 3. Return to the website. 4. Open the order detail page. |  | 1. CyberSource returns success result. | Antank QA Team | SIT | 2026-07-10 | Evan | As expected | Pass | 520382111111111
SIT | SIT-TC-WEB-BCO-010 | Website / Discount / CyberSource Checkout | Medium | High | Signed scope F8 / Q-6 | CyberSource cancellation or timeout returns safely | Verify that when a user cancels payment or payment times out in CyberSource, the website does not mark the order as paid. | Order has a valid promo code applied and Checkout has been launched. | 1. Enter the CyberSource payment flow. 2. Cancel payment or trigger payment timeout. 3. Return to the website or wait for callback. 4. Open the order detail page. |  | 1. The order remains Pending Payment, Payment Failed, or Cancelled according to the product rule. 2. Tickets are not issued. 3. The promo-code record does not create a successful payment effect. 4. The user can enter the payment flow again. | Antank QA Team | SIT | 2026-07-08 | Evan | As expected | Pass
SIT | SIT-TC-WEB-BCO-011 | Website / Discount / Ticket Scope | Medium | Medium | PRD background | Promotion applies only to ticket orders | Verify that the bank-card offer activity supports ticket promotion only and does not apply to non-ticket product orders. | Non-ticket product or non-ticket order entry exists; the same promo code is configured for ticket promotion. | 1. Open a non-ticket product order confirmation page. 2. Enter the ticket promo code. 3. Click Confirm or Apply. 4. Wait for the promo-code validation result. |  | 1. The non-ticket order does not apply the offer. 2. The order amount remains unchanged. 3. The system either shows the promo code as unavailable or hides the entry point according to the actual UI. | Antank QA Team | SIT | 2026-07-08 | Evan | As expected | Pass
SIT | SIT-TC-WEB-BCO-012 | Website / Discount / Regression Smoke | Medium | Medium | Q-1/Q-4 | Normal ticket purchase is unaffected when no promo code is entered | Verify that the ordinary ticket purchase Checkout flow is not blocked when the new promo-code entry exists but no promo code is entered. | Ticket item supports bank-card offer activity; user does not enter any promo code. | 1. Open the order confirmation page. 2. Leave the promo-code field empty. 3. Click Checkout. 4. Complete ordinary CyberSource payment or enter the payment flow. |  | 1. The user can continue to Checkout. 2. The order is paid at the non-discounted amount. 3. The ordinary ticket purchase main flow is not affected. | Antank QA Team | SIT | 2026-07-08 | Evan | As expected | Pass
SIT | SIT-TC-WEB-BCO-013 | Website / Discount / Amount Integrity | High | High | Q-8 / F7 | Discounted amount matches payment amount | Verify that the website discount calculation amount, Checkout payment amount, and paid order amount are consistent. | Valid promo code has been applied and a CyberSource successful payment can be completed. | 1. Record original amount, discount amount, and discounted payable amount. 2. Click Checkout and complete payment. 3. Open the payment return page and order detail page. | PROMO-MID-OK + CS-SUCCESS-CARD | 1. The Checkout amount equals the discounted payable amount shown on the order confirmation page. 2. The paid order amount is consistent after payment succeeds. 3. The system does not charge the original amount while displaying a discount on the website. | Antank QA Team | SIT | 2026-07-08 | Evan | As expected | Pass
SIT | SIT-TC-WEB-BCO-014 | Website / Discount / Retry Path | Medium | Medium | F8 / Q-6 | User can retry payment or modify promo code after payment failure | Verify that after CyberSource payment failure returns to the website, the user can retry payment or return to the order confirmation page to modify the promo code. | Order has a promo code applied and one failed payment can be completed with a failure test card. | 1. Trigger one CyberSource payment failure. 2. Return to the order or failure page. 3. Try to repay or modify the promo code. | CS-FAIL-CARD | 1. The order remains unpaid or failed. 2. The user can restart payment or return to modify the promo code. 3. The system does not generate a duplicate successful order or ticket. | Antank QA Team | SIT | 2026-07-08 | Evan | As expected | Pass
SIT | SIT-TC-WEB-BCO-015 | Website / Discount / Traceability | Medium | Medium | F7/F8 / Q-6 | Order detail retains promo-code and payment-result traceability | Verify that after payment completes, the order detail or available backend record can trace the promo code, discount amount, and CyberSource return result. | Order uses a promo code and completes one successful or failed payment. | 1. Complete one successful or failed payment. 2. Open the order detail page or available backend query page. 3. Open the promo-code, discount amount, and payment result record area. | PROMO-MID-OK + success/fail return code | 1. Promo code or activity identifier is recorded. 2. Discount amount or non-effective reason is recorded. 3. CyberSource success or failure return result is recorded. 4. The record supports later defect analysis and evidence submission. | Antank QA Team | SIT | 2026-07-08 | Evan | As expected | Pass